## Road Map
Completed Fall Semester 2021
Spring Semester 2022 Releas 1
Spring Semester 2022 Release 2
Will Complete if time in Spring Semester
Inwood Bagels - Road Map
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration1 - Mar 4 | Iteration 2 - Apr 1 | Iteration 3 - Apr 22 | Iteration 4 - May 13
01. Login/Registration | 01.01 Register new customer user | 5
| 01.02 View Account Details | 3
| 01.03 User login | 5
| 01.04 Admin Login | 5 |  | X
| 01.05 Create Admin Account | 5 |  | X
| 01.06 Update admin account details | 3 |  |  |  | X
| 01.07 Update user account detais | 3 |  |  |  | X
| 01.08 Reset password | 3 | X
02. Menu Management | 02.01 Add/Delete menu item | 5 |  |  | X
| 02.02 Edit menu item cost/description | 5 |  |  |  | X
| 02.03 Set pick up times | 3 |  | X
03. Order & Cart Management | 03.01 View menu | 5
| 03.02 Choose menu item | 5
| 03.03 Add / remove item(s) to cart | 8 | X
| 03.04 View past orders | 5
| 03.05 Re-order food | 5
| 03.06 Modify order | 5
| 03.07 Display items/total price in cart | 3 | X
| 03.08 Display number of items in cart | 3 | X
| 03.09 Place Order | 5
| 03.10 Order Received | 5
| 03.11 Search menu item | 5 |  |  | X
| 03.12 Accept/reject order | 8
| 03.13 Add to favorites | 5
| 03.14 Choose pick up or delivery | 3 |  |  | X
| 03.15 Choose pick up time | 3 |  | X
04. Rewards Management | 04.01 Earn rewards | 5
| 04.02 Use rewards | 5
| 04.03 Accept Rewards | 5
| 04.04 Give Rewards | 5
05. Payment Preferences | 05.01 Add credit or debit card | 8 |  |  |  | X
| 05.02 Choose pay online / in-person | 3 |  |  | X
| 05.03 Payment complete | 8
| 05.04 Validate payment with stripe | 8
06. Inventory Management | 06.01 Track items sold | 8
| 06.02 Track low stock items | 8
| 06. 03 Update inventory with recently purchased items | 8
07. Notifications | 07.01 Notify of order status | 3
| 07.02 Notify of order received | 3
| 07.03 Notify of order accepted/rejected | 3
| Velocity : | 198 | 17 | 16 | 16 | 19

## Story Map
Inwood Bagels - User Story Map
EPICS | Users | Epic 1 - Login/Registration | Epic 2 - Menu Management | Epic 3 - Order & Cart Management | Epic 4 - Rewards Management | Epic 5 - Payment Preferences | Epic 6 - Inventory Management | Epic 7 - Notifications
01. Login/Reigstration |  |  |  | 03.03 Add/remove item(s) to cart
02. Menu Management |  |  |  | 03.07 Display items/total price in cart
03. Order & Cart Management |  | 01.08 Reset Password |  | 03.08 Display number of items in cart |  |  |  |  | Iteration 1
04. Rewards Management |  | 01.04 Admin Login | 02.03 Set pick up times | 03.15 Choose pick up time
06. Inventory Management |  | 01.05 Create Admin Account
07. Notifications | [8 empty] | Iteration 2
|  |  | 02.01 Add/Delete Menu item | 03.11 Search Menu item |  | 05.02 Choose pay online / in-person
|  |  |  | 03.14 Choose pick up or delivery |  |  |  |  | Iteration 3
|  | 01.06 Update admin account details | 02.02 Edit menu item cost/description |  |  | 05.01 Add credit or debit card
|  | 01.07 Update user account details | [6 empty] | Iteration 4