## R2 I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2: I3 | 03. Order & Cart management | 3.14 | Choose pick up or delivery | Implement GUI | 2022-04-01 | 2022-04-07 | 100% | Hemaswi
2 |  |  |  |  | Implement core functionality | 2022-04-01 | 2022-04-07 | 100% | Gaelle
3 |  |  |  |  | Implement system interface in crosscut | 2022-04-01 | 2022-04-07 | 100% | Gaelle
4 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-01 | 2022-04-07 | 100% | Abhilash & Brinda
5 |  |  |  |  | Execute Test Cases | 2022-04-01 | 2022-04-07 | 100% | Abhilash & Brinda
6 |  |  |  |  | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Gaelle
7 |  | 02. Menu Management | 2.01 | Add/Delete Menu item | Implement GUI | 2022-04-01 | 2022-04-07 | 100% | Hemaswi
8 |  |  |  |  | Implement core functionality | 2022-04-01 | 2022-04-07 | 100% | Gaelle
9 |  |  |  |  | Implement entitlements, data flow out, data driven validation, and connectivity crosscuts | 2022-04-01 | 2022-04-07 | 100% | Gaelle
10 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-01 | 2022-04-07 | 100% | Abhilash & Brinda
11 |  |  |  |  | Execute Test Cases | 2022-04-01 | 2022-04-07 | 100% | Abhilash & Brinda
12 |  |  |  |  | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Abhilash
13 |  | 03. Order & Cart management | 3.11 | Search menu item | Implement GUI | 2022-04-07 | 2022-04-22 | 100% | Hemaswi
14 |  |  |  |  | Implement core functionality | 2022-04-07 | 2022-04-22 | 0% | Gaelle
15 |  |  |  |  | Implement data flow in and connectivity crosscutting concerns | 2022-04-07 | 2022-04-22 | 0% | Gaelle
16 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-07 | 2022-04-22 | 0% | Abhilash & Brinda
17 |  |  |  |  | Execute Test Cases | 2022-04-07 | 2022-04-22 | 0% | Abhilash & Brinda
18 |  |  |  |  | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Gaelle
19 |  | 01. Login/Registration | 1.06 | Update user account details | Implement GUI | 2022-04-07 | 2022-04-22 | 100% | Hemaswi
20 |  |  |  |  | Implement core functionality | 2022-04-07 | 2022-04-22 | 0% | Gaelle
21 |  |  |  |  | Implement Entitlements, and Connectivity crosscuts | 2022-04-07 | 2022-04-22 | 0% | Gaelle
22 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-07 | 2022-04-22 | 0% | Abhilash & Brinda
23 |  |  |  |  | Execute Test Cases | 2022-04-07 | 2022-04-22 | 0% | Abhilash & Brinda
24 |  |  |  |  | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Charles

## R2 I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2:I4 | 05. Payment Preferences | 5.02 | Choose pay online / in-person | Implement GUI | 2022-04-22 | 2022-04-29 | 0% | Hemaswi
2 |  |  |  |  | Implement core functionality | 2022-04-22 | 2022-04-29 | 0% | Gaelle
3 |  |  |  |  | Implement entitlements crosscutting concerns | 2022-04-22 | 2022-04-29 | 0% | Gaelle
4 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-22 | 2022-04-29 | 0% | Abhilash & Brinda
5 |  |  |  |  | Execute Test Cases | 2022-04-22 | 2022-04-29 | 0% | Abhilash & Brinda
[5 empty] | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Nandu
6 |  |  | 5.01 | Add credit or debit card | Implement GUI | 2022-04-29 | 2022-05-12 | 0% | Hemaswi
7 |  |  |  |  | Implement core functionality | 2022-04-29 | 2022-05-12 | 0% | Gaelle
8 |  |  |  |  | Implement Entitlements, and Connectivity crosscuts | 2022-04-29 | 2022-05-12 | 0% | Gaelle
9 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-29 | 2022-05-12 | 0% | Abhilash & Brinda
10 |  |  |  |  | Execute Test Cases | 2022-04-29 | 2022-05-12 | 0% | Abhilash & Brinda
[5 empty] | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Noah
11 |  | 02. Menu Management | 2.02 | Edit menu item cost/description | Implement GUI | 2022-04-29 | 2022-05-12 | 0% | Hemaswi
12 |  |  |  |  | Implement core functionality | 2022-04-29 | 2022-05-12 | 0% | Gaelle
13 |  |  |  |  | Implement Entitlements, and Connectivity crosscuts | 2022-04-29 | 2022-05-12 | 0% | Gaelle
14 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-29 | 2022-05-12 | 0% | Abhilash & Brinda
15 |  |  |  |  | Execute Test Cases | 2022-04-29 | 2022-05-12 | 0% | Abhilash & Brinda
[5 empty] | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Hemaswi
16 |  | 01. Login/Registration | 1.07 | UpdateAdmin Account Details | Implement GUI | 2022-04-22 | 2022-04-29 | 0% | Hemaswi
17 |  |  |  |  | Implement core functionality | 2022-04-22 | 2022-04-29 | 0% | Gaelle
18 |  |  |  |  | Implement Entitlements, and Connectivity crosscuts | 2022-04-22 | 2022-04-29 | 0% | Gaelle
19 |  |  |  |  | Develop test cases for GUI, core functionality, and crosscutting concerns | 2022-04-22 | 2022-04-29 | 0% | Abhilash & Brinda
20 |  |  |  |  | Execute Test Cases | 2022-04-22 | 2022-04-29 | 0% | Abhilash & Brinda
[5 empty] | Create Use Case Specification | 2022-04-01 | 2022-04-07 | 100% | Brinda