## Sheet1
Fall 2021 Semester
[7 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 - Midterm Exam | 9 | 10 | 11 | 12 | 13 | 14 - Final Exam | 15
[7 empty] | Date | 2021-09-14 | 2021-09-21 | 2021-09-28 | 2021-10-05 | 2021-10-12 | 2021-10-19 | 2021-10-26 | 2021-11-02 | 2021-11-09 | 2021-11-16 | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 2021-12-21
Project Phase | Deliverables |  | Assigned To: | Start Date | End date | Status | Progress in %
Project Planning | Project Proposals |  | Gaelle | 2021-09-14 | 2021-09-17 | Finished | 100%
| Create Two Business cases |  | Gaelle and Hemaswi | 2021-09-17 | 2021-09-21 | Finished | 100%
| Create a project initiaion document (PID) |  | Team | 2021-09-21 | 2021-09-28 | Finished | 100%
| Create Project plan / complete PID (add RACI) |  | Team | 2021-10-01 | 2021-10-05 | Finished | 100%
| Begin Home Page Development |  | Masha | 2021-09-28 | 2021-10-05 | Finished | 100%
Milestone 1: Project plan completed (Subject to change)
Requirements | Create BRM diagram and user roles |  | Charles | 2021-10-05 | 2021-10-12 | Finished | 100%
| Create Context diagram and system interface table |  | Nandu | 2021-10-05 | 2021-10-12 | Finished | 100%
| Complete Requirement types |  | Nandu | 2021-10-05 | 2021-10-12 | Finished | 100%
| Complete Business Requirements |  | Charles | 2021-10-12 | 2021-10-19 | Finished | 100%
| Complete Functional Decomposition and fishbone diagram |  | Nandu | 2021-10-12 | 2021-10-19 | Finished | 100%
| Create RCT |  | Nandu | 2021-10-12 | 2021-10-19 | Finished But Late | 100%
| Create Menu for Home Page |  | Masha | 2021-10-12 | 2021-10-19 | Finished | 100%
| Select features to implement THIS SEMESTER in RCT |  | Gaelle and Charles | 2021-10-19 | 2021-10-26 | Finished | 100%
| UML analysis diagrams |  | Nandu | 2021-10-19 | 2021-10-26 | Finished | 100%
| Data-flow diagram (logical) |  | Nandu | 2021-10-19 | 2021-10-26 | Finished | 100%
| Complete Functional requirements for user stories |  | Nandu | 2021-10-19 | 2021-10-26 | Finished | 100%
| Home Page Demo completed |  | Masha | 2021-10-19 | 2021-10-26 | Finished | 100%
Milestone 2: Requirements Completed
High-Level Design | Complete ER diagrams |  | Noah | 2021-10-26 | 2021-11-09 | Finished | 100%
| Complete Database table specs |  | Noah | 2021-10-26 | 2021-11-09 | Finished | 100%
| Complete a physical Data-flow diagram |  | Nandu | 2021-10-26 | 2021-11-09 | Finished | 100%
| Complete 2 Architecture diagrams |  | Masha and Noah | 2021-11-09 | 2021-11-16 | Finished | 100%
| Establish Github projects |  | Team | 2021-11-09 | 2021-11-16 | Finished | 100%
Milestone 3: High-Level Design completed
Implementation/Coding | Create Admin Test Table |  | Gaelle | 2021-11-14 | 2021-11-17 | Finished | 100%
| Create Customer Test Table |  | Abhilash | 2021-11-14 | 2021-11-17 | Finished | 100%
| Create Item Test Table |  | Charlie | 2021-11-14 | 2021-11-17 | Finished | 100%
| Create Menu Test Table |  | Hemaswi | 2021-11-14 | 2021-11-17 | Finished | 100%
| Class Diagram (UML) |  | Masha | 2021-11-16 | 2021-11-30 | Finished | 100%
| Complete Sequence Diagram(UML) |  | Masha | 2021-11-16 | 2021-11-30 | Finished | 100%
| Source code uploaded to Github, executable code ready for testing |  | Masha | 2021-11-16 | 2021-12-06 | Finished | 100%
| Populate Test Data in database |  | Noah | 2021-11-17 | 2021-11-30 | Finished | 100%
Coding
| View Menu | GUI & Functionality Design | Masha and Hemaswi | 2021-11-02 | 2021-11-09 | Finished | 100%
|  | Coding | Masha and Hemaswi
| Choose Menu Item | GUI & Functionality Design | Masha and Hemaswi
|  | Coding | Masha and Hemaswi
| Register new customer user | GUI & Functionality Design | Masha and Hemaswi | 2021-11-09 | 2021-11-16 | Finished | 100%
|  | Coding | Masha and Hemaswi
| Display Price | GUI & Functionality Design | Masha and Hemaswi | 2021-11-16 | 2021-11-23 | Finished | 100%
|  | Coding | Masha and Hemaswi
| User Login | GUI & Functionality Design | Masha and Hemaswi | 2021-11-23 | 2021-11-30 | Finished | 100%
|  | Coding | Masha and Hemaswi
| Account Details | GUI & Functionality Design | Masha and Hemaswi | 2021-11-30 | 2021-12-05 | Finished | 100%
|  | Coding | Masha and Hemaswi
| Choose Delivery method | GUI & Functionality Design | Masha and Hemaswi | 2021-12-05 | 2021-12-14 | Finished | 100%
|  | Coding | Masha and Hemaswi
Milestone 4: Implementation/Coding completed
Testing | Plan and complete test plan document |  | Abhilash and Brinda | 2021-10-26 | 2021-11-09 | Finished | 100%
| View Menu | Design Test Cases | Abhilash and Brinda | 2021-11-30 | 2021-12-05 | Finished | 100%
|  | Execute Test Cases | Abhilash and Brinda
|  | Analyze Test Results | All
| Choose Menu Item | Design Test Cases | Abhilash and Brinda | 2021-11-30 | 2021-12-05 | Finished | 100%
|  | Execute Test Cases | Abhilash and Brinda
|  | Analyze Test Results | All
| Register new customer user | Design Test Cases | Abhilash and Brinda | 2021-11-30 | 2021-12-05 | Finished | 100%
|  | Execute Test Cases | Abhilash and Brinda
|  | Analyze Test Results | All
| Display Price | Design Test Cases | Abhilash and Brinda | 2021-11-30 | 2021-12-05 | Finished | 100%
|  | Execute Test Cases | Abhilash and Brinda
|  | Analyze Test Results | All
| User Login | Design Test Cases | Abhilash and Brinda | 2021-11-30 | 2021-12-05 | Finished | 100%
|  | Execute Test Cases | Abhilash and Brinda
|  | Analyze Test Results | All
| Account Details | Design Test Cases | Abhilash and Brinda | 2021-12-05 | 2021-12-14 | Finished | 100%
|  | Execute Test Cases | Abhilash and Brinda
|  | Analyze Test Results | All
| Choose Delivery method | Design Test Cases | Abhilash and Brinda | 2021-12-14 | 2021-12-18 | Finished | 100%
|  | Execute Test Cases | Abhilash and Brinda
|  | Analyze Test Results | All
Milestone 5: Testing completed
Presentation | Prepare for presentation |  | Team | 2021-12-07 | 2021-12-21 | Finished | 100%
Project Completion | [6 empty] | 100%